## Clarification Log
haha
Clarification Log
Document Title: Clarification Log
Activity ID: M1.5
Date: 10/04/25
Project Team ID: TP802 – S2 – 3
Project Team Name: Team 3
Date | Question/Clarification Needed | Response/Decision | Status
2025-04-10 | Which social media platforms should be integrated in the MVP? | Focus on Instagram and YouTube for MVP. Twitter/X and LinkedIn as stretch goals. | Open
2025-04-10 | What metrics are most important to track for influencer engagement? | Engagement rate, reach, conversion rate, ROI, and audience growth. Sentiment analysis as a secondary metric. | Open
2025-04-10 | Do we need real-time analytics or is daily/weekly reporting sufficient? | daily/weekly reporting sufficient?Daily data aggregation is sufficient for MVP. Consider adding near-real-time for v2. | Open
2025-04-10 | Should the system support multiple user roles (admin, manager, viewer)? | Yes, implement role-based access control with at least 3 permission levels. | Open
2025-04-10 | What authentication method should we implement? | OAuth 2.0 with support for SSO through Google and Microsoft accounts. | Open
2025-04-10 | Should we prioritize mobile responsiveness or develop a separate mobile app? | Focus on responsive web design first. Native mobile app development can be considered for future versions. | Open
2025-04-10 | What is the expected data retention period for historical performance data? | Store detailed data for 18 months, aggregated data for 5 years. | Open
2025-04-10 | What export formats should be supported for reports? | PDF, Excel, and CSV formats are required. API access for data export is a stretch goal. | Open